## Sheet1
Risk | Risk Reduction Techniques | Likelihood | Impact | Risk Exposure
Personnel shortfalls | Staff with top talent; job matching; teambuilding; training and career development; early scheduling of key personnel | 7 | 7 | 49
Unrealistic time and cost estimates | Multiple estimation techniques; design to cost; incremental development; recording and analysis of past projects; standardization of methods | 3 | 8 | 24
Developing the wrong software functions | Improved software evaluation; formal specification methods; user surveys; prototyping; early user manuals; software functions are going to be chosen by me therefore are not a large risk. | 2 | 6 | 12
Late changes to requirements | Incremental development, define key requirements early, formal process for adding another requirement. | 5 | 4 | 20
Performance problems | Conduct optimizing, debug parts of the program to identify slow areas. | 4 | 8 | 32
Language data is inaccurate. | Gather data from reputable sources, keep sentences simple. | 7 | 5 | 35